## BoQ
Belmont Road Play Area, Northwich
Bills of Quantity May 2024
A Preliminaries/General Requirements
Item | Description | No. | Unit | Rate | £ p
A1 | To bring and remove from site, all plant required for the works. | 1 | item | included | included
A2 | The setting out and taking levels of all works as specified and required through the implementation of the works | 1 | item |  | 0
A3 | Design and resolution time on site which may arise | 1 | item | included | included
A4 | Provision, erection, maintenance and removal on completion of all offices, mess rooms, stores, workshops and ancillary items required by the contractor. Exact location for site compound and storage areas to be agreed with Contract Administrator. | 1 | item |  | 0
A5 | Making good any external works not included within this contract which may be damaged by the contractor during the contract period, including making good the compound area. Compound area to be adjacent to the play area on the grass and area made good upon completion. | 1 | item | included | included
A6 | All necessary warning signs, pedestrian detours and barriers to be used during the contract. Price to include for all hoardings necessary to provide screening and safety for the other site users. Adjacent roads and pavements to be kept clear and free of mud and debris at all times. | 1 | item |  | 0
A7 | Determining the whereabouts of any existing structures and services and their protection during the contract period. This may mean hand digging rather than machine due to proximity of services to surface level. | 1 | item |  | 0
A8 | Detailed dilapidation/photographic record of existing boundaries, pavements and roads around the site to be undertaken by CA with contractor | 1 | item | included | included
TOTAL FOR PAGE |  |  |  |  | 0
C20 Demolition / Site Clearance
Item | Description | No. | Unit | Rate | £ p
C20.1 | Existing equipment - remove following existing play equipment and furniture from play area and take from site to contractors tip for recycling. Include for removal and disposal of associated concrete footings and pads. | ___ | ___ | ___
a | litter bin, plastic approx. 500mm dia | 1 | no. |  | 0
b | bench without back | 1 | no. |  | 0
c | large swing frame with 6 posts set into concrete | 1 | item |  | 0
d | remains of metal frame from swinging unit (with 6 posts set into ground with concrete) | 1 | item |  | 0
e | large timber trim trail/adventure unit with tower and net | 1 | item |  | 0
f | large junior metal multi play unit | 1 | item |  | 0
g | large dished roundabout | 1 | item |  | 0
h | toddler springie board with sail | 1 | item |  | 0
I | toddler slide unit | 1 | item |  | 0
j | springie | 1 | item |  | 0
C20.2 | Existing kneerail (PROV QTY) - removal of existing timber kneerail from along the site boundary with Belmont Road and take arisings from site to contractors tip for recycling. Kneerail height approx. 600mm. | 50 | lin.m |  | 0
C20.3 | Sleeper walls (PROV QTY) - removal of existing timber sleeper walls from edge of earth mounds within the play area site. Wall consists of sleepers on end at an average height of 600mm. | 40 | lin.m |  | 0
C20.4 | Existing bitmac path (PROV QTY) - remove existing bitmac path from Rushton Close and excavate to a depth of 200mm. Path width 1200mm. All arisings to be taken from site to contractors tip. | 20 | m² |  | 0
C20.5 | Sand filled grass mats (PROV QTY) - remove existing sand filled grass mat surfacing from beneath play equipment in 2 different locations. Include for excavating the sand to a depth of 150mm. Arisings to be taken from site to contractors tip for recycling. | 300 | m² |  | 0
C20.6 | Excavation for sand filled carpet surfacing (PROV QTY) - undertake excavation to an approx. depth of 270mm to create level base for surfacing. Arisings to be used on site to extend the existing earth mound alongside the kick about area. Depth of excavation will vary depending on the fall height of the specific play unit. | 690 | m² |  | 0
C20.7 | Excavation for path and bitmac surfacing - undertake excavation to a depth of 300mm to create base for path and hard surfacing. Arisings to be used in mound creation at a later date, alongside the kick about area. | 57 | m² |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q Paving/Planting/Fencing/Site Furniture
Q10 Stone/concrete/brick kerbs/edgings/channels
Item | Description | No. | Unit | Rate | £ p
Q10.1 | Concrete pin kerbs for play area (PROV QTY) - supply and install new concrete pin kerbs around area to be surfaced with grass mat. Pin kerbs to be 50x100mm, bedded and haunched with concrete. Include for all excavations and use of arisings in mound creation alongside the football pitch edge. Concrete haunching on 'inside' to be set neatly at 10mm below top of kerb to allow new grass mat surfacing to be glued onto it securely. | 175 | lin.m |  | 0
Q10.2 | Concrete pin kerbs for path (PROV QTY) - supply and install new concrete pin kerbs to edges of new bitmac paths into the play area. Pin kerbs to be 50x100mm, bedded and haunched with concrete. Include for all excavations and use of arisings in mound creation alongside the football pitch edge. Edges of kerbs to be made good with topsoil and grass seed. | 60 | lin.m |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q20 Granular sub bases to roads/pavings
Item | Description | No. | Unit | Rate | £ p
Q20.1 | Sub base for sand filled carpet surfacing - supply and lay geotextile membrane, 200mm mot type 1 to create subbase for surfacing in play area | 690 | m² |  | 0
Q20.2 | Base for sand filled carpet surfacing - supply and lay 50mm depth of 40mm clean stone to create base for surfacing in the play area (as per manufacturers guidance) | 690 | m² |  | 0
Q20.3 | Sub base for bitmac path - supply and lay geotextile membrane, 100mm mot type 1 to create subbase for new bitmac surfaced path | 57 | m² |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q21 In situ concrete roads/pavings/bases - ALL ITEMS ARE PROVISIONAL
Item | Description | No. | Unit | Rate | £ p
Q21.1 | Concrete steps - supply materials and create shuttered concrete steps leading towards play area from Marlow Road. Steps to be 1200mm wide with risers at 150mm high. Treads to be approx. 400mm deep. Include for all excavations and preparation required, including mot base and geotextile. | 20 | no. |  | 0
Q21.2 | Concrete paths - supply materials and create shuttered concrete path extending each end of new steps at 1200mm wide. Concrete to be 100mm deep and join with existing bitmac path at the top. Include for all excavations and preparation required, including mot base and geotextile. | ___ | ___ | ___
a | path at top of steps | 8 | lin.m |  | 0
b | path at bottom of steps | 2 | lin.m |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q22 Coated macadam/asphalt roads/pavings
Item | Description | No. | Unit | Rate | £ p
Q22.1 | Bitmac base to pedestrian path - supply and lay 70mm dense binder course to newly prepared path base to create new pedestrian path into play area. Path width to be 1500mm. Include for making good the new bitmac surface up to existing; ensuring the joint is secure. | 57 | m² |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q26 Special surfacings/pavings for sport/general amenity
Item | Description | No. | Unit | Rate | £ p
Q26.1 | Sand filled carpet (PROV QTY) - supply and lay sand filled carpet in a range of colours to prepared base and secure to the haunching of newly installed concrete edgings. Carpet to be filled with play sand. To include for the relevant material, laid to correct depths to suit fall height of each unit. To be installed according to manufacturers guidance. Confirmation of supplier/subcontractor and sample to be provided for approval before ordering. | ___ | ___ | ___
a | Fjord blue | 140 | m² |  | 0
b | Navy blue | 240 | m² |  | 0
c | Marine green | 70 | m² |  | 0
d | Lavender | 240 | m² |  | 0
Q26.2 | Resin bound gravel - supply and lay buff/gold colour resin bound gravel surfacing to prepared bitmac path base to a depth of 20mm up to concrete edgings. Colour to be agreed with NTC. | 57 | m² |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q28 Topsoiling
Item | Description | No. | Unit | Rate | £ p
Q28.1 | Making good (PROVISIONAL ITEM AND QTY) - make good areas of disturbed ground around edges of the site and within the site with 100mm topsoil. Topsoil to be raked and prepared, free from any stone larger than 40mm. | 300 | m² |  | 0
Q28.2 | Earth mounds - include for creating/extending earth mound between the play area and kickabout area using excavated material from site and for shaping the mound to have gently sloping sides suitable for mowing. Mounds to be made good for wildflower seeding with 50mm topsoil. Approximate area - 100m2. | 1 | m² |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q30 Seeding and Turfing
Item | Description | No. | Unit | Rate | £ p
Q31.1 | Wildflower seeding - supply and sow 'Tuscan Hills' perennial wildflower seed mix to earth mound along kickabout area to make good. To be sown at a rate of 2g/m2 between September and May. Include for raking and preparing the ground and sowing as per suppliers instructions. | 100 | m² |  | 0
Q31.2 | Grass seeding (PROV QTY) - supply and sow amenity grade grass seed to make good areas of ground disturbed by the works and compound area. Include for preparing ground and raking to a fine tilth, removing all large stones and debris. | 300 | m² |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q40 Fencing
Item | Description | No. | Unit | Rate | £ p
Q40.1 | Steel kneerail (PROV QTY) - supply and install new galvanised steel kneerail at 600mm high along front of the site, replacing old timber kneerail taken out earlier. Include for all excavations and concrete required and for making good the ground around each post with topsoil and grass seed. | 50 | lin.m |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q50 Site/street furniture/equipment
Item | Description | No. | Unit | Rate | £ p
Q50.1 | Litter bin INSTALL ONLY- installation only of 82l litter bins with galvanised steel liner and timber exterior. Exact location to be agreed on site. Bins to be Big Ben from Play and Leisure (EABB) in green with green liner. To be supplied with extended posts for root fixing with concrete. Dimensions 570mm dia and 860mm high. Include for all excavations and concrete required. To be supplied by Northwich Town Council. | 2 | no. |  | 0
Q50.2 | Picnic table - installation only of accessible steel picnic table. Table to be 'Cambridge' from Play and Leisure (SFB7), provided by Northwich Town Council. To be installed as per manufacturers instructions. Include for all materials required for installation. | 3 | no. |  | 0
Q50.3 | Bench - installation only of steel bench to play area. Seat to be 'York' bench from Play and Leisure (SFB1), provided by Northwich Town Council. To be installed as per manufacturers instructions. Include for all materials required for installation. | 2 | no. |  | 0
Q50.3 | Collection - collection of all equipment and furniture as needed from Northwich Town Council offices and take to site for installation. Allow for several collections as needed. | 1 | item |  | 0
Q50.4 | CCTV post - Supply and install into 1m depth concrete foundations 80mm diameter, 6m in length, 4mm wall thickness, red oxide finish, painted black with specialty metal paint to one post. | 1 | item |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
Q52 Play and sports equipment systems
Item | Description | No. | Unit | Rate | £ p
Q52.1 | New play equipment - installation only of the following play equipment to the new play area. Equipment to be purchased by Northwich Town Council and delivered to their yard. To be installed as per manufacturers instructions. Please note - this equipment is budget dependent; some of the units may be omitted. | __ | __ | ___
a | Kompan 2 seat flat swings KSW902 | 1 | item |  | 0
b | Kompan 3 seat wings with cradle and you/me/inclusive seats KSW903 | 1 | item |  | 0
c | Kompan accessible play unit PCM103031 | 1 | item |  | 0
d | Kompan Talk and Tumble play panel PCM000421 | 1 | item |  | 0
e | Kompan Trampoline JUM10401 | 1 | item |  | 0
f | Kompan spheres at 345mm dia SUR13207-172 | 1 | item |  | 0
g | Kompan spheres at 500mm dia SUR13207-251 | 1 | item |  | 0
h | Kompan spheres at 345mm dia SUR13207-347 | 1 | item |  | 0
I | Kompan glue for spheres SUR18490-000 | 1 | item |  | 0
j | Kompan ground anchors for spheres SUR13297 | 3 | no. |  | 0
k | Kompan Element small dished roundabout ELE400024 | 1 | item |  | 0
l | Kompan Swan springer M17401 | 1 | item |  | 0
m | Kompan posts for sensory panels EN-FIRPSQ | 1 | item |  | 0
n | Kompan play panel Roller Ball TPP280025-041 | 1 | item |  | 0
o | Kompan play panel Kaleidoscope TPP280027-04 | 1 | item |  | 0
p | Kompan play panel Sensory multi play panel TP280024-0401 | 1 | item |  | 0
q | Kompan communication boards EN-FAL | 2 | nr. |  | 0
r | Play and Leisure River Thames multiplay unit R110 | 1 | item |  | 0
s | Play and Leisure Mountain Esk multiplay unit R116 | 1 | item |  | 0
p | Play and Leisure Vortex overhead rotator QU91 | 1 | item |  | 0
u | Play and Leisure Quest Orbitor rotator QU90 | 1 | item |  | 0
v | Play and Leisure Comet seesaw QU80 | 1 | item |  | 0
w | Play and Leisure balance beam TT10 | 1 | item |  | 0
x | Play and Leisure Burmah bridge TT14 | 1 | item |  | 0
y | Play and Leisure Overhead rings TT04 | 1 | item |  | 0
z | Play and Leisure Chain walk TT01 | 1 | item |  | 0
aa | Play and Leisure Wobble Log TT13 | 1 | item |  | 0
bb | Sutcliffe accessible roundabout SIR000 | 1 | item |  | 0
Q52.2 | Collection - collection of all equipment and furniture as needed from Northwich Town Council offices and take to site for installation. Allow for several collections as needed. | 1 | item |  | 0
Q52.3 | Post Installation health and safety inspection - order and arrange independent post installation inspection for entire play area in consultation with Clerk at Northwich Town Council. A copy of the report should be made available as soon as it has been produced. | 1 | no. |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
R13 Drainage
Item | Description | No. | Unit | Rate | £ p
R13.1 | Trampoline drainage (PROV ITEM) - supply and install soakaway immediately beneath trampoline (approx. 1500x1500x500mm), consisting of geotextile membrane and clean drainage stone. | 1 | item |  | 0
TOTAL FOR PAGE |  |  |  |  | 0
TOTALS CARRIED FORWARD
A | Preliminaries/general requirements |  |  |  | 0
C20 | Demolition / Site Clearance |  |  |  | 0
Q10 | Stone/concrete/brick kerbs/edgings/channels |  |  |  | 0
Q20 | Granular sub bases to roads/pavings |  |  |  | 0
Q21 | In situ concrete roads/pavings/bases |  |  |  | 0
Q22 | Coated macadam/asphalt roads/pavings |  |  |  | 0
Q26 | Special surfacings/pavings for sport/general amenity |  |  |  | 0
Q28 | Topsoiling |  |  |  | 0
Q31 | External planting |  |  |  | 0
Q40 | Fencing |  |  |  | 0
Q50 | Site/street furniture/equipment |  |  |  | 0
Q52 | Play and sports equipment systems |  |  |  | 0
R13 | Drainage |  |  |  | 0
Total carried to form of tender |  |  |  |  | 0
Company Name
Signed by
Telephone
Address
Length of time for completion
Anticipated start date: